## Sheet1
# | Name# | Skill sets and area | Artifacts to be produced | End Goal | Timeline | Latest status as on 5/22 | Latest status as on 5/23 | Latest status as on 5/24 | Latest status as on 5/25
1 | Srinivas | Selenium framework, Jenkins and DevOps | 1. Architecture diagram and documentation for framework. 2. framework itself including devops components. | Publish framework that works with Jenkins and GitHub | 1. Architecture diagram and documentation for framework : 29th May'19 2. framework itself including devops components : 4th Jun'19 | 1. POM framework is ready with sample test cases. 2. Created an sampleMaven Project with BDD framework. | 1. STAF framework is imported 2. Installtion process is in progress 3. Maven errors are being resolved | 1. STAF framework is imported 2. Installtion process is in progress 3. Maven errors are being resolved | 1. STAF framework is in progress 2. Adhoc Request that are worked for Today : 1. Consolidated “Testing Achievements - 2018-19” for STR 2. In search and worked on “Reference applications for the POC/Demos” which is requested by Abhishek
2 | Nikhil | Selenium framework, Jenkins and DevOps | 1. Architecture diagram and documentation for framework. 2. framework itself including devops components. | Publish framework that works with Jenkins and GitHub | 1. Architecture diagram and documentation for framework : 29th May'19 2. framework itself including devops components : 4th Jun'19 | 1. POM framework is ready with sample test cases. 2. Created an sampleMaven Project with BDD framework. | Automated the login page by identifying the page elements into one class and tried to automate the login functionality | 1. Today I tried to add a book to the shopping cart and complete the order. 2. For that I have identified all the required page elements into different classes and started writing the step definitions. 3. Writing of step definitions is in progress. | Completed writing step definitions and facing exceptions while executing. Resolving in progress
3 | Ramesh | UFT framework and Python | 1. Generic UFT framework for webservices or any web application 2. Self Learning Python and Should be preparing an understanding document | 1. Publishing framework( Provided UFT License is there) 2. Would be ready to take up any project related to python | 1. 15 to 20 Days 2. 25 to 30 Days | This is an update from Ramesh on the today's task across email. Same is copied below: Currently I am going through Python Video’s and other articles related to python. Apart from that, I shall prepare “Basic SQL concepts and documentation for the same with examples “ by 28th May. |  |  | Python – Learned data types of python – Lists , Tuples and Practiced it declaring the same.
4 | Junaid | Testing concepts ,Python ,Machine Learning POC | Documentation of core Machine learning concepts and R, Documentation of Modeling Using R function and libraries | POC of Modeling and Implementations of Machine Learning algorithms. | 1. POC : 7th June | R Basics And Data Types - Arrays, List,Vectors,Operations,Data Frames and Descriptive Statistics |  | Introduction to RPA, Introduction to UI Path and Installed UI path tool | * UiPath – Understanding User Interface Components *Recording and Playback functionality. *Automating the task of copying data from a website and writing into excel file.
5 | Kamna | Database testing/ETL Testing, Jmeter,Selenium Framework | 1. KT Documents/Class Room session for ETL Testing 2. Jmeter : Process to setup the project and Documentaion | 1. KT Documents/Class Room session for ETL Testing 2. Jmeter : Process to setup the project and Documentaion | 1. ETL Testing : 28th May'19 2. Jmeter : 5th Jun'19 | 1. Git Hub repository creation 2. KT on GitHub to team Action Item for tomorrow : 1. Documentation for GitHub | On Leave | GiTHub document is added and sent for Review. Working DatabaseTesting related document with Ramesh | Working on Database testing document. Studying shell Scripting. I have scheduled a unix session .
6 | Shanth | RPA Automation, DevOps stacks involving selenium automation | RPA primer for the team to get started on using RPA tool(UiPath), User friendly documentation for the team to use in house published STAF framework for selenium automation | Build team capability to work on UiPath RPA tool, Provide inhouse expertise to leverage published automation framework for open source selenium along with Jenkins and Github integration | 1. RPA primer -31st May 2. STAF framework -7th June